No-Cost Extension for Smart Policing

Grant #2009-DG-BX-0118

The Los Angeles Police Department (LAPD) requests a six-month no-cost extension for the BJA grant, Smart Policing in the Los Angeles Police Department

Amount of additional time needed: The current end date for the project is June 30, 2014 and we request an extension until December 31, 2014.

Why the extension is necessary:

Operation LASER has been expanded to include seven patrol divisions and Air Support Division.  In addition to Newton Division (the original location for Smart Policing), Captains at Devonshire, Foothill, Hollenbeck, Southwest, Topanga, Wilshire, and Air Support have agreed to implement the model.  This means crime analysts, officers, and detectives from these divisions will be trained over the next six months.  With the completion of the training room at RACR Division with Smart Policing funds, staff  will receive training on Palantir and the Omega Dashboard, both of which are essential to crime and intelligence analysis.

In addition, the Research Partner, Justice & Security Strategies, will collect and analyze data for these divisions for evaluation purposes.

What you intend to do in the extended time:

An extension will allow us to continue to train staff and evaluate the impact of Operation LASER in seven patrol divisions and Air Support Division.